## Release Plan
Effort Break-up for BACNet Activity SCHED-E-B
Activity No | Start Date | Completion Date | Acitvity Name | Activity descriptions | Effort in Days
1 | 2013-09-10 | 2013-10-08 | Profile Modification
|  |  |  | Adding new objects to existing BACnet build | 3
|  |  |  | Adding the service for new objects | 2
|  |  |  | Modify the profile Application for adaptation on new objects (Non Persistance) | 2
|  |  |  | Add the machnism to porfile for Scheduler and Calander object persistance | 5
|  |  |  | Polarsoft Stack Porting | 2
|  |  |  | Application and Stack interface modification | 4
|  |  |  | Unit test and Release notes etc.. | 2
|  |  | Release V0.1 | This relase will help the FPG team to do VAR and VAL on Profile |  | This Release will contain 1. Create Schedular and Calander Object wrt to profile.bin 2. Access the Schedular and Calander object Servicess 3. Modification on these Object will be persistance
2 | 2013-10-09 | 2013-11-08
|  |  |  | Schedular services creation | 2
|  |  |  | Logic implemantation for Schedular Object | 10
|  |  |  | Link the schedular to various object properties | 10
|  |  | Release V0.2 | Internal relase
3 | 2013-11-11 | 2013-11-15
|  |  |  | Uint test and bug fixing | 5
|  |  | Release V1.0 | Relase to Verification
4 | 2013-11-18 | 2013-12-04 |  | Verification and Bug fixing | 10
|  |  |  | Release prepration and Integration to Bacnet development streem | 3