## Estimates
Estimates - BACNet Activity
|  | Total Estimated Effort in man Months | 2.425
|  | Total Estimated Cost in Kilo Euros | 8.8512
Activity No | Acitvity Name | Activity descriptions | Effort in Weeks | Remarks
1 | SCHED-E-B
|  | Profile API functions to create BACnet Schedule and Calendar objects | 1 | FPG release Must needed to start with
|  | Interface for Stack and Application | 1
|  | Algorithm implementation to trigger the scheduler | 2 | PolarSoft Stack Must needed to start with
|  | storage of schedule and calendar objects in non-volatile memory | 1 | FPG release Must needed to start with
|  | Stack modification/addition to support the SCHEDULE and Calender object | 1
2 | Release to Verification | Unit/Integration/Release | 0.5
3 | Convergence for Final Release | Verification & Bug Fixes | 2
4 | Final Release | Release | 0.2 | Assumption: Release of Binaries through FTP/shared location.
5 |  | Project Buffer | 1
|  | Total Effort in weeks ==> | 9.7
|  | Total Effort in man Months ==> | 2.425